## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-01-09 |  |  |  |  | January | [27 empty] | February
Scrolling Increment: | 1 | time axis 2023-01-10 to 2023-03-06
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-01-10 to 2023-03-06
Documentation
Gantt Chart | On Track | Gabriel | 50% | 2023-01-09 | 42
Entity Relation Diagram |  | Gabriel |  | 2023-01-19 | 3
Use Case Diagram |  | Gabriel |  | 2023-01-24 | 6
PowePoint Slides | On Track | Gabriel |  | 2023-01-19 | 15
TITLE 2
Setting up the Server | On Track | Endrit | 100% | 2023-01-11 | 4
Database - Creation | On Track | Endrit | 100% | 2023-01-12 | 6
Database - Populating | On Track | Endrit | 100% | 2023-01-13 | 8
API - Login |  | Christian/Stanley | 100% | 2023-01-12 | 6
API - Registration |  | Christian/Stanley | 100% | 2023-01-19 | 5
API - Add Contact |  | Christian/Stanley
API - Search Contact | On Track | Christian/Stanley |  | 2023-01-24 | 5
API - Edit Contact |  | Christian/Stanley
API - Delete Contact | On Track | Christian/Stanley | 100% | 2023-01-23 | 2
Frontend
Design
Login/Signup Page |  |  | 100% | 2023-01-12 | 7
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-01-24 |  |  |  |  | January | [6 empty] | February | [27 empty] | March
Scrolling Increment: | 1 | time axis 2023-01-25 to 2023-03-21
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2023-01-24 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2023-01-29 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2023-01-21 | 10
Task 4 | Milestone |  |  | 2023-02-13 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2023-01-30 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-01-30 | 13
Task 2 | On Track |  | 50% | 2023-02-01 | 9
Task 3 | Low Risk |  | 33% | 2023-02-06 | 11
Task 4 | Milestone |  |  | 2023-02-08 | 1 | bar: W
Task 5 |  |  |  | 2023-02-09 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-02-08 | 4
Task 2 | Med Risk |  |  | 2023-02-11 | 14
Task 3 | On Track |  |  | 2023-02-26 | 6
Task 4 | Goal |  |  | 2023-03-02 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2023-01-30 | 19
TITLE 4
Task 1 |  |  |  | 2023-03-05 | 15
Task 2 |  |  |  | 2023-03-19 | 5
Task 3 | Milestone |  |  | 2023-04-30 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-01-24 |  |  |  |  | January | [6 empty] | February | [27 empty] | March
Scrolling Increment: | 5 | time axis 2023-01-29 to 2023-03-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-01-29 to 2023-03-25
TITLE 1
Task 1 | Goal | Name | 25% | 2023-01-24 | 3
Task 2 | Milestone |  |  | 2023-01-29 | 1 | bar: 2023-01-29
Task 3 | Low Risk |  | 50% | 2023-01-21 | 10
Task 4 | Milestone |  |  | 2023-02-13 | 1 | bar: 2023-02-13
Task 5 | Med Risk |  | 10% | 2023-01-30 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-01-30 | 13
Task 2 | On Track |  | 50% | 2023-02-01 | 9
Task 3 | Low Risk |  | 33% | 2023-02-06 | 11
Task 4 | Milestone |  |  | 2023-02-08 | 1 | bar: 2023-02-08
Task 5 |  |  |  | 2023-02-09 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-02-08 | 4
Task 2 | Med Risk |  |  | 2023-02-11 | 14
Task 3 | On Track |  |  | 2023-02-26 | 6
Task 4 | Goal |  |  | 2023-03-02 | 3 | 2023-03-02: 2; 2023-03-03: 2; 2023-03-04: 2
Task 5 | Low Risk |  |  | 2023-01-30 | 19
TITLE 4
Task 1 |  |  |  | 2023-03-05 | 15
Task 2 |  |  |  | 2023-03-19 | 5
Task 3 | Milestone |  |  | 2023-04-30 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one